## RN (36-400 kV)
ELLEVIO PROJECT FORECAST, UPDATED February 2024
RN Stockholm
Area | Project | Category field work | RFP to market / Prequalifcation | Project value | Ellevio prequalification system used *
RN Stockholm | Förnyelse Kårsta, Orkesta (Vallentuna 4 trafobyte) 20/10kV | Renewal of switchgear | 2024-02-01 | < 50 MSEK | X
RN Rural | TT60 Myggenäs Nytt 40kV stv, 1st ny 16MVA 40/10kV trafo | Renewal of switchgear | 2024-03-01 | < 50 MSEK | X
RN Stockholm | Förbifart Stockholm 33kV Bredäng + Stensätravägen | Cable excavation | 2024-03-01 | <100 MSEK
RN Rural | TT90 Skärhamn 40/10 kV stn | Renewal of switchgear | 2024-03-01 | < 50 MSEK | X
RN Rural | Ny 30 kV ledning Skived-Molkom (ML14), ca 18 km | New overheadline | 2024-03-01 | < 50 MSEK | X
RN Rural | Tandö station 400/145 kV ex power transformer | New switchgear | 2024-03-01 | <100 MSEK
RN Stockholm | FS Högberga 70 kV | Renewal of switchgear | 2024-04-01 | < 50 MSEK | X
RN Stockholm | Anslutning Beckomberga 33kV | cable excavation | 2024-04-01 | < 50 MSEK | X
RN Rural | Öna. 50/10 kV ombyggnation | Renewal of switchgear | 2024-04-24 | < 50 MSEK | X
RN Rural | TL15 TL19 Myggenäs-Åker Kopplingstorn. Kabelprojekt, 40 kV | Cable excavation | 2024-05-01 | < 25 MSEK | X
RN Stockholm | Brunkeberg 110/11 kV | Renewal of switchgear | 2024-05-01 | <200 MSEK
RN Rural | Njutånger Stamnätsstation 400 / 130 kV (exkl trafo) | New switchgear | 2024-06-01 | <100 MSEK
RN Rural | 170 kV ledning, L57 Malung, L58 Lyberget (2*12 km) | New overheadline | 2024-06-01 | <100 MSEK
RN Stockholm | Fs-Salo 110/33 kV | New switchgear | 2024-08-01 | <100 MSEK
RN Stockholm | New station in Bromsten. 110/10kv. 3 Trafos. | New switchgear | 2024-08-01 | <200 MSEK
Windpower | Gäddtjärn stamnätstation | New switchgear | 2024-09-01 | <200 MSEK
Windpower | Gäddtjärn parkstationer (2 eller 3) | New switchgear | Q4-24 | < 50 MSEK | X
RN Rural | L183 Älvdalen-Väsa | New overheadline | Q4-24 | < 25 MSEK
Windpower | Ölme-Kvarnberg ledning, 145 kV | New overheadline | Q4-24 | < 50 MSEK | X
RN Rural | Tandö Nyhusen ledning 170kV ( exkl Trästolpar) | New overheadline | Q1-25 | <100 MSEK
RN Rural | Otterbäcken, Ny station 130/20kV | New switchgear | TBD | < 50 MSEK
Windpower | Ölme-Kvarnberg-Broby stationer | New switchgear | TBD | < 50 MSEK
Windpower | Södra Valla Solpark station | New overheadline | TBD | < 50 MSEK
Ellevio AB vill upplysa om att de meddelanden som här följer enbart utgör en prognos om möjliga upphandling. Ellevio AB åtar sig inte i och med publicerandet av informationen nedan att göra formenliga upphandlingar. Informationen utgör inte ett meddelande om förhandsannonsering.
NOTERA: Vindkraftsprojekt kommer presenteras i mer detalj separat, projekten på denna lista är de som förväntas komma i närtid.
Ellevio AB emphasizes that information submitted here is to be considered as a forecast about possible procurements. Ellevio AB is not obligated to to realize these procurements. The information is not to be considered as a prior information notice.
NOTE: Windpower projects will be presented in more detail separately, those projects that are presented here are those who are expected to come in near time.
* Ellevio AB använder ett kvalificeringssystem för att på förhand välja ut leverantörer som ska få delta i upphandlingar avseende Entreprenad med kontraktsvärde mellan 20-55 MSEK
* Ellevio AB is using a qualification system to pre-select suppliers for tenders of construction works with contract value between 20 and 55 MSEK.

## LN (0,4-24 kV)
ELLEVIO PROJECT FORECAST, UPDATED February 24
Area | Project | Category field work | RFP to market | Project value | Ellevio prequalification system used *
LN Rural | Västkusten Kablifiering 0,4-10 kV | Cable excavation | 2024-03-01 | < 50 MSEK | X
LN Stockholm | 11kV Cedergrensvägen | Cable excavation | 2024-04-01 | < 50 MSEK | X
LN Rural | Gävleborg Kablifiering 0,4-20kV | Cable excavation | 2024-04-01 | < 50 MSEK
LN Stockholm | Djurgårnskablar | Cable excavation | 2024-04-01 | < 50 MSEK | X
LN Rural | Dalarna Kalblifiering 0,4-20kV | Cable excavation | 2024-08-01 | < 50 MSEK | X
LN Stockholm | FS Sånga/ FS Munsö | Cable excavation | 2024-08-01 | < 50 MSEK | X
LN Stockholm | Utbyggnad Rågsved/Hagsätra | Cable excavation | 2024-09-01 | < 50 MSEK | X
LN Stockholm | Kablifiering Älvsjö_Stureby_Bandhagen | Cable excavation | 2024-09-01 | <100 MSEK
LN Stockholm | Fs Djursnäs Ombyggnation | Cable excavation | Q4-24 | < 50 MSEK | X
LN Stockholm | Fs Sorunda Ombyggnation | Cable excavation | Q4-24 | < 50 MSEK | X
Ellevio AB vill upplysa om att de meddelanden som här följer enbart utgör en prognos om möjliga upphandling. Ellevio AB åtar sig inte i och med publicerandet av informationen nedan att göra formenliga upphandlingar. Informationen utgör inte ett meddelande om förhandsannonsering.
Ellevio AB emphasizes that information submitted here is to be considered as a forecast about possible procurements. Ellevio AB is not obligated to to realize these procurements. The information is not to be considered as a prior information notice.

## Longterm plan Station Stockholm
Site | Voltage (kV) | Scope | Start & finish - Execution | Budget
Tp Liljeholmen | 110/33/11/0,4 | New station and switchgear | ca 2025-2027 | >350 MSEK
Fs Perstorp | 33/11 (110) | New station and cable | TBD | >100 MSEK
Fs Bredäng | 220 | renewal station | 2027-2029 | TBD